## Slide 1: POST-EVENT TOLLGATE Precision Dynamics Project for Delivery and Quality Improvement
DeFranco Performance Solutions LLC

## Slide 2: Problem Statement
Voice of The Customer
Metrics
Scrap Rate (%)
Measurements
Good people, but quality is inconsistent. We've had to scrap batches because parts don't meet spec. Delivery dates slip constantly too. We want to keep working with them, but if tolerances don't tighten up and lead times become predictable, we'll have to find another supplier. Frustrating because they're responsive when we call
On Time Delivery (%)
Dimensional Variation (mm)
Lead Time (days)
First Pass Yield (%)
±0.008"
10%
14 days average
Target
<2%
78%
78%
±0.003”
10 days
98%
88%
Precision Dynamics experiences inconsistent quality (88% first pass yield, 10% scrap rate), missed deadlines (78% on-time delivery, 14-day lead time), and dimensional variation (±0.008" versus ±0.003" target), threatening customer retention and profitability.

## Slide 3: Business Impact and projected improvement
Business Impact Statement
Precision Dynamics loses approximately $2.66M annually from quality defects, production delays, excess inventory, and rework cycles. Improving first pass yield to 98%, on-time delivery to 95%, and lead time to 10 days could recover $2.2M+ in hard and soft savings.
Defects (10% scrap rate, $100/part):
  1,200 parts/month × $100 = $120,000/month
Overproduction (78% OTD = missed deadlines, excess inventory):
  15% overrun × $75/unit = $45,000/month
Waiting (production delays from rework):
  5 workers × $45/hr × 2 hrs/day = $18,000/month
Extra Processing (rework cycles):
  200 rework events × $50 labor + $30 material = $16,000/month
Inventory Carrying (WIP buildup from delays):
  $180K inventory × 15% carry rate ÷ 12 = $22,500/month
Total Monthly Loss: ~$221,500
Annualized: ~$2.66 Million

## Slide 4: Scope
Suppliers
Inputs
Processes
Material receiving & inspection
Outputs
Customers
Finished precision parts
Raw materials (sheets, bars)
Allegheny Technologies (raw materials)
Haas Automation (CNC equipment)
Mitutoyo (inspection tools)
Kennametal (cutting tools)
Customer specifications/drawings
Production schedules
Calibration standards
CNC machining
Quality inspection
Rework (if needed)
Packaging & shipping
Inspection reports
Shipping documentation
Scrap/waste logs
Lockheed Martin (aerospace assemblies)
Collins Aerospace (avionics components)
Spirit AeroSystems (structural parts)
Raytheon Missiles & Fire Control (defense systems)
In Scope:
Actual machining processes between material prep and packing
Out of Scope:
Logistics, customer contracts, labor

## Slide 5: Value Stream Map
Material Prep & Stage
CT: 15m
C/O: 30m
CNC rough
CT: 20m
C/O: 120m
CNC finish
CT: 45m
C/O: 25m
CT: 10m
C/O: 15m
Surface Treatment
CT: 20m
C/O: 25m
Final Assembly
Inspection
CT: 12m
C/O: 10m
WIP: 80 units
WIP: 120 units
WIP: 45 units
WIP: 8 units
WIP: 10 units
WIP: 5 units
Demand: 500 units a month
Freight to hub
50 units/3 days
Order to warehouse
125 units a week
80 units
2-day buffer
10 units
2-day hold

## Slide 6: Improvement Schedule
Pre-Event
Present the problem and requesting to begin a deeper analysis.
Event
Present the analysis, and permissions to implement proposed solutions
Post-Event
Present results of improvements and permission to implement control plan
(This Presentation)
Estimated Project Duration: 6 weeks

## Slide 7: Team and Call to Action
We are seeking your authorization to proceed with a comprehensive analysis of this issue.
Executive Sponsor:
  Mark Richardson, Plant Manager
Project Owner:
  Jerry DeFranco, DPS-Lean Consultant
Process Owner:
  David Morales, CNC Supervisor
Team:
  Sarah Chen, Quality Engineer
  Miguel Vasquez, Maintenance Technician
  Jennifer Kowalski, Production Planner
  Antonio Garcia, CNC Operator
Commitment
  Kaizen Week Commitment - Three half days 1st week of June
  Pre-Event / Post-Event – 10% time

## Slide 8: Process Map
Job Release
Tool Setup & Inspection
Workpiece Clamping
Spindle Start & Warm-up
Rough Cut Pass
Finish Cut Pass
Tool Retract & Coolant Flush
Dimensional Verification
Part Unload & Destack
Changeover Setup
Pull work order from queue
Waiting (120-unit backlog)
Load cutting tools, calibrate
Motion (searching for correct tools)
Secure part in chuck/fixture
Motion (manual alignment)
Spindle ramp to speed
Waiting (no overlap with prep)
Initial material removal
Defects (tool chatter, poor surface finish)
Final precision cut to tolerance
Extra Processing (over-engineered passes)
Cool spindle, clear chips
Waiting (manual coolant management)
Caliper/micrometer check at machine
Overproduction (redundant—caught at QC anyway)
Remove from chuck, stage for inspection
WASTE: Motion (parts travel 30 feet to staging)
Clean machine, swap fixtures for next job
Transportation + Changeover (75-minute avg)
Critical DOWNTIME Drivers:
Tool setup variability (15 mins variance)
Manual spindle warm-up (5 mins non-value)
Changeover (75 mins) — longest single constraint
Waiting for upstream material (queue time)

## Slide 9: Failure Mode Effects and Analysis
Step Seq | Step | Failure Mode | Note | SEV | OCC | DET | SEV Score | OCC Score | DET Score | RPN
1 | Job Setup | Workpiece Slip in Chuck | Worn jaws, low clamping pressure | Serious effect | Occasional failures | Formal auditing | 9 | 4 | 8 | 288
2 | Tool Magazine | Tool Not Located/Wrong Index | Carousel misalignment, sensor failure | High effect | Relatively few failures | Automated rejection | 7 | 3 | 2 | 42
3 | Tool Changer | Tool Installation Collision | Worn carousel, interference angle | Serious effect | Relatively few failures | None | 9 | 2 | 10 | 180
4 | Tool Touch-Off | Offset Entry Error | Manual key-in mistake, calibration drift | High effect | Occasional failures | Gauging sample | 7 | 5 | 5 | 175
5 | Coolant Flow | Coolant Starvation | Drain blockage, pump cavitation | Moderate effect | Moderate failure rate | Visual population | 6 | 6 | 6 | 216
6 | Spindle Ramp | Speed Overshoot/Undershoot | VFD lag, belt slip, motor fault | Moderate effect | Occasional failures | Automated warning | 6 | 4 | 3 | 72
7 | First Depth Pass | Tool Chatter & Vibration | Worn spindle bearings, improper feed | Very high effect | Frequent failures | Visual sample | 8 | 7 | 7 | 392
8 | Mid-Pass Check | Missed Chatter Detection | Operator distraction, noise masking | High effect | Occasional failures | Informal checks | 7 | 5 | 9 | 315
9 | Final Depth Pass | Out-of-Tolerance Rough | Tool deflection, thermal growth | Serious effect | Moderate failure rate | Gauging sample | 9 | 6 | 5 | 270
10 | Tool Retract | Tool Breakage on Withdraw | Collision, stuck tool, misalignment | Catastrophic | Relatively few failures | None | 10 | 3 | 10 | 300

## Slide 10: Root Cause Analysis
WORKPIECE SLIP IN CHUCK (RPN: 288)
Clamping pressure lost
Tool Chatter (RPN: 392)
Chuck jaws worn
No replacement schedule exists
Reactive maintenance culture
No predictive monitoring system
Spindle runout excessive
Bearings not inspected
No PM interval defined
Spindle life unknown
No maintenance data system
Missed Chatter Detection (RPN: 315)
Shop noise masks alarm
No acoustic warning system
Budget prioritizes production
No visibility to defect cost
No monthly KPI dashboard
Out-of-Tolerance rough (RPN: 270)
Tool deflects under load
Feed rate too aggressive
No load monitoring
No spindle load sensor
Capital budget insufficient; ROI unclear
Tool Breakage on Withdraw (RPN: 300)
Collision with workpiece
Tool offset incorrect
Carousel sensor drifts
No daily calibration routine
Setup SOP vague; operator variance
Defects at final CNC
Core Issue
Failure Mode
Why 1
Why 2
Why 3
Why 4
Why 5

## Slide 11: Top 10 Implementations
Initiative | Impact (1–10) | Effort (1–10) | RPN
Add in-process gauging at first depth pass | 10 | 6 | 60
Add collision detection software for tool changer | 8 | 7 | 56
Program adaptive feed rate control | 8 | 7 | 56
Implement tool presetter with auto-populated offset entry | 9 | 6 | 54
Use torque-verified clamping with automated pre-cycle verification | 9 | 6 | 54
Install combined vibration and acoustic emission sensor | 9 | 6 | 54
Replace worn spindle bearings (highest RPN: 392) | 10 | 5 | 50
Conduct SMED event targeting the 75-minute changeover | 10 | 5 | 50
Thermal mapping to build spindle growth compensation model | 8 | 6 | 48
Implement pull system with kanban-controlled WIP cap | 9 | 5 | 45

## Slide 12: Responsibility Matrix
Improvement initiative | R — Responsible | A — Accountable | C — Consulted | I — Informed | Est. cost | Est. Benefits | Est. completion
Replace worn spindle bearings | M. Vasquez | M. Richardson | S. Chen, J. DeFranco | D. Morales, A. Garcia | $3,500–$6,000 | Hard: $28,000 Soft: $10,800 | 6/1/2026
Conduct SMED event — 75-min changeover | J. DeFranco | M. Richardson | D. Morales, A. Garcia | J. Kowalski, S. Chen | $1,000–$2,500 | Soft: $27,000 | 6/1/2026
Add in-process gauging at first depth pass | S. Chen | M. Richardson | A. Garcia, M. Vasquez | D. Morales, J. DeFranco | $8,000–$15,000 | Hard: $36,000 Soft: $9,600 | 7/1/2026
Implement tool pre-setter with auto-populated offset entry | J. DeFranco | M. Richardson | A. Garcia, S. Chen | D. Morales, J. Kowalski | $5,000–$12,000 | Hard: $21,000 Soft: $13,500 | 7/1/2026
Install combined vibration and acoustic emission sensor | M. Vasquez | M. Richardson | J. DeFranco, S. Chen | D. Morales, A. Garcia | $4,000–$9,000 | Hard: $15,000 Soft: $18,000 | 7/1/2026
Add collision detection software for tool changer | J. DeFranco | M. Richardson | M. Vasquez, A. Garcia | D. Morales, S. Chen | $3,000–$7,000 | Hard: $18,000 | 8/1/2026
Program adaptive feed rate control | J. DeFranco | M. Richardson | A. Garcia, S. Chen | D. Morales, M. Vasquez | $2,000–$5,000 | Hard: $12,000 Soft: $9,000 | 8/1/2026
Torque-verified clamping with automated pre-cycle check | M. Vasquez | M. Richardson | S. Chen, A. Garcia | D. Morales, J. DeFranco | $4,500–$10,000 | Hard: $34,560 | 8/1/2026
Thermal mapping — spindle growth compensation model | S. Chen | M. Richardson | M. Vasquez, J. DeFranco | D. Morales, A. Garcia | $1,500–$4,000 | Hard: $16,200 Soft: $4,800 | 9/1/2026
Implement pull system with kanban-controlled WIP cap | J. DeFranco | M. Richardson | J. Kowalski, D. Morales | S. Chen, A. Garcia | $500–$1,500 | Hard: $27,000 Soft: $21,600 | 9/1/2026
We are seeking your authorization to proceed with these improvements.
Cost
$33k-$72k
Total Savings
$208,560 Direct
$114,300 Capacity
Daily Standup 10 minutes
Weekly Retrospective 30 minutes
Monthly Demonstration 30 minutes

## Slide 13: KPI IMPACT
Metric | Before | After | Target
First Pass Yield | 88% | 96.2% | 98%
Scrap Rate | 10% | 3.8% | <2%
On-Time Delivery | 78% | 91% | 95%
Lead Time | 14 days | 11 days | 10 days
Dimensional Variation | ±0.008" | ±0.004" | ±0.003"
Changeover Time | 75 min | 38 min | —
Monthly Scrap Cost | $120,000 | $45,600 | —
WIP Inventory Value | $180,000 | $112,000 | —

## Slide 14: DEFECT IMPACT
Failure Mode | RPN Before | RPN After | Reduction
Tool chatter and vibration | 392 | 112 | −280 (71%)
Missed chatter detection | 315 | 70 | −245 (78%)
Tool breakage on retract | 300 | 60 | −240 (80%)
Workpiece slip in chuck | 288 | 72 | −216 (75%)
Out-of-tolerance final pass | 270 | 90 | −180 (67%)
Coolant starvation | 216 | 72 | −144 (67%)
Tool installation collision | 180 | 36 | −144 (80%)
Offset entry error | 175 | 35 | −140 (80%)
Speed overshoot/undershoot | 72 | 36 | −36 (50%)
Tool not located/wrong index | 42 | 21 | −21 (50%)

## Slide 15: FINANCIAL IMPACT (ANNUAL)
Waste Category | Before | After | Hard Savings | Soft Savings
Defects (scrap) | $1,440,000 | $547,200 | $892,800 | —
Overproduction | $540,000 | $270,000 | $270,000 | —
Waiting | $216,000 | $97,200 | — | $118,800
Extra processing | $192,000 | $76,800 | $57,600 | $57,600
Inventory carrying | $270,000 | $168,000 | $102,000 | —
Total | $2,658,000 | $1,159,200 | $1,322,400 | $176,400
Annual net savings: $1,498,800

## Slide 16: Replaced worn spindle bearings

## Slide 17: Added in-process gauging at first depth pass

## Slide 18: Completed a Single Minute Exchange of Die project (SMED)

## Slide 19: Control Plan
Control Item | Type | R — Responsible | A — Accountable | C — Consulted | I — Informed | Target Date
Shadow board for changeover tooling sequence | Visual Management | A. Garcia | D. Morales | J. DeFranco | M. Richardson | Oct 2026
Kanban card system for WIP cap at each station | Visual Management | J. Kowalski | D. Morales | J. DeFranco | M. Richardson, S. Chen | Oct 2026
SPC control charts posted at first depth pass station | Visual Management | S. Chen | D. Morales | J. DeFranco | M. Richardson | Oct 2026
Torque verification checklist laminated at chuck station | Mistake Proofing | M. Vasquez | D. Morales | S. Chen | A. Garcia, M. Richardson | Oct 2026
Offset entry lockout requiring presetter confirmation before cycle start | Mistake Proofing | J. DeFranco | D. Morales | A. Garcia, M. Vasquez | M. Richardson, S. Chen | Nov 2026
Coolant drain cleaning PM trigger tied to cycle count, not calendar | Mistake Proofing | M. Vasquez | D. Morales | S. Chen | M. Richardson | Nov 2026
First article inspection checklist — mandatory sign-off before production run | Procedure | S. Chen | D. Morales | A. Garcia | M. Richardson, J. Kowalski | Nov 2026
Standardized changeover SOP with time targets per step | Procedure | J. DeFranco | D. Morales | A. Garcia, J. Kowalski | M. Richardson | Nov 2026
Spindle warm-up and ramp sequence documented and posted at machine | Procedure | M. Vasquez | D. Morales | A. Garcia | M. Richardson, S. Chen | Nov 2026
Operator certification training on new gauging, presetter, and sensor systems | Training | J. DeFranco | M. Richardson | S. Chen, D. Morales | J. Kowalski, A. Garcia | Nov 2026
We are seeking your authorization to proceed with these improvements.